## One Fed
Building Level Interventions
Instructions: Enter any identified building-level interventions that impact energy usage and emissions. Interventions may include operational changes, retrofits, enhancements to existing capital plans, electrification, and on-site renewables. All boxes for a given intervention should be populated. To optimize for user friendliness, order the interventions based on the earliest possible year of intervention, moving from earliest to latest. Interventions should be identified by the building's engineering team in coordination with Paul Rode and the TS sustainability team. Formatting: Additional Up-Front Costs and Additional Opex should be stated in negative terms and should be priced on a "relative to business as usual" basis (i.e. only state the price in excess of a business as usual scenario). If there is no lifespan, enter "No Lifespan" to indicate this. If the building does not use a certain energy type, enter "0" for the expected reduction. Change in energy consumption should be entered as a negative value if there is a reduction in consumption associated with the intervention and as a positive value if there will be an increase in consumption. If there is an earliest possible date when an intervention can be launched, enter this year in the "Earliest Possible Date" column. If not, enter the current year in this field.
Building | Savings | Order | Intervention Name | Description of Measure | Intervention Type | Additional Up-Front Cost (Net rebates from utilities or state energy offices, or federal programs) | Up Front Cost: Capex or R&M | Change in Electricity Consumption Reduction (kWh) | Change in Natural Gas Use(MMBtu) | Change in Steam Consumption, kLbs | Useful Life/Lifespan | Earliest Possible Year | Change in Opex (O&M) | Energy Savings Passthrough? | Sources (Citations, Links, Consulting Reports, etc.)
One Federal | Heating & Cooling & Base | 1 | Retrocommissioning (RCx) | Complete BMS commissioning | Retrofit | 9000000 | R&M | 0.05 | 0 | 0.05 | 10 | 2025 | 0 | No | RCx proposals
One Federal | Heating & Cooling | 2 | Optimal Start Stop | Sequence implementation in BMS | Retrofit | 65000 | R&M | 0.01 | 0 | 0.01 | 12 | 2024 | 5000 | No | Controls Vendor
One Federal | Cooling | 3 | Chiller Plant Optimization | Analytic Program ontop of BMS | Retrofit | 8000000 | R&M | 0.04 | 0 | 0 | 12 | 2024 | 5000 | No | Optimun Energy
One Federal | Base | 4 | Elevator energy revovery | Optional add to elevator package | Capital Project Enhancement | 200000 | Capex | 0.005 | 0 | 0.005 | 25 | 2035 | 0 | No | Schindler
One Federal | Cooling | 5 | DriveLine Retrofits | Electric driveline for chillers | Electrification | 3000000 | Capex | 1.25 | 0 | 1 | 30 | 2028 | -10000 | No | York
One Federal | Cooling | 5 | New Electric Chillers | Electric Chillers | Electrification | 8000000 | Capex | 1.25 | 0 | 1 | 30 | 2028 | -25000 | No | York
One Federal | Base | 6 | DHW to Point of Use | At bathroom upgrades | Capital Project Enhancement | 380000 | R&M | 1.05 | 0 | 1 | 12 | 2024 | 0 | No | Eng
One Federal | Heating & Cooling | 7 | Façade air stopping | caulking and general air stopping | Retrofit | 2000000 | R&M | 0.01 | 0 | 0.01 | 15 | 2023 | 0 | No | Eng
One Federal | Heating & Cooling | 8 | New High Efficiency Windows | New Windows tripple pane R6@30SHG | Capital Project Enhancement | 22958333.3333 | Capex | 0.06 | 0 | 0.06 | 10 | 2028 | 0 | No | Eng
One Federal | Heating & Cooling | 9 | Spandrel and column insulation | Insulation at TI's | Capital Project Enhancement | 1000000 | Capex | 0.005 | 0 | 0.01 | 15 | 2024 | 0 | No | Eng
One Federal | Heating | 10 | Electric Risistance Coils & ASHP | AHU coils, and ASHP hot water for induction systems | Electrification | 19200000 | Capex | 1.7 | 0 | 1 | 40 | 2030 | 25000 | No | Eng
One Federal | Heating | 10 | Electric Risistance Coils & ElectricHW Boiler | AHU coils, and elect HW boiler for induction systems | Electrification | 5200000 | Capex | 1.9 | 0 | 1 | 40 | 2030 | -10000 | No | Eng
One Federal | Heating | 10 | Electric Steam Boiler | Electric boiler | Electrification | 2500000 | R&M | 2 | 0 | 1 | 15 | 2026 | -35000 | No | Eng

## Sheet1
Heating
Cooling
Base
Heating & Cooling
Heating & Cooling & Base