## Sheet1
California Comerical Properties NCZ capital stragtegyies
Site | Intervention Name | Description of Measure | Intervention Type | Additional Up-Front Cost (Net rebates from utilities or state energy offices, or federal programs) | Capex or R&M | year
160 Spear | Retrocommissioning (RCx) | All systems + corrections | Retrofit | 36420 | R&M | 2027 | scheduled for after major leasing changes
| New High Eff Chiller Plant | Equipment Enhansement | Capital Proejct Enhancement | 320000 | Capex | 2030 | Enhansment adds pumps, optimization controls and heat recovery chiller option
| Façade air stopping | wet seal window IGU's | Retrofit | 400000 | R&M | 2024 | being done this year
| Heating converstion to ASHPHW | ASHP producting HW heat | Capex | 2230000 | Cpaex | 2029 | Roof mounted on new dunnage connection to HW system directly below (this is the textbook ASHP converstion project)
| Pneumatic to DDC converstion | BMS DDC expansion | Capital Proejct | 400000 | Capex | 2029 | meant to coinside with leasing turns
One Bush
| Retrocommissioning (RCx) | Complete BMS commissioning | Retrofit | 35861.64 | R&M | 2026 | scheduled to happen after new chiller start up and new tower start up
| Exhaust Air Heat Recivery | Exhaust air heat recovery coil | Retrofit | 365000 | Capex | 2030
| DHW to Point of Use | Electrificaiton | Electrification | 315000 | Capex | 2027 | Currently steam
| ASHP for HW heating | Recover heating hot water from CT | Electrification | 5420700 | Capex | 2036 | Another textbook ASHP project due to building geometry
| ASHP for CW and HW production | Add CW production to ASHP | Electrification | 6233805 | Capex | 2030 | This is timed to be a substitue for a chiller replacement (there are 2 in one bush, one is new this year, the other 50 year old chiller will not be replaced in kind. Could deduct cost of chiller job from this which is 1200,000
222 Second
| Retrocommissioning (RCx) | Complete BMS commissioning | Retrofit | 35000 | R&M | 2027 | Timing based on RCx after building segeration to multi-tenant
| Central ASHP to Hot Water | Electrificaiton | Electrification | 2750000 | Capex | 2040 | Another textbook conversion.
333 Bush
| Optimun Start / Stop | Controls with ML program | Retrofit | 118000 | R&M | 2027 | control enhancement pland for take place beofore major cooling projects
| Pumping Optizmation Controls | VFD's Controls with ML program | Retrofit | 225000 | Capex | 2026 | controls and vfd proejct
| Chiller Plant part load chiller | Installation of a pony chiller | Capital Project | 1000000 | Capex | 2026 | this is operational and efficiency
| Chiller end of life replacement | Chiller plan replacement | Capital Project Enhancement | 250000 | Capex | 2030 | EOL enhancement for highest efficiency chiller that is available and passes cost means test
| Elevator energy revovery | Elevator Mod with energy recovery | Capital Project Enhancement | 240000 | R&M | 2030 | timed with mod
| Heating Electrification via ASHP's | Electrificaiton | Electrificaiton | 8000000 | R&M | 2040 | Very difficulte job, may end up going electric boiler.
595 Market
| Retrocommissioning (RCx) | Complete BMS commissioning | Retrofit | 60000 | R&M | 2025 | This can be done next year or the following.
| Elevator energy revovery | Optional add to elevator package | Capital Project Enhancement | 25000 | Capex | 2035 | Scheduled for the next mod
| Façade air stopping | Caulking and general air stopping | Retrofit | 2300000 | R&M | 2030 | scheduled based on sealent life.
| New High Efficiency Windows | New Windows tripple pane R6@30SHG | Capital Project Enhancement | 2400000 | Capex | 2040 | Note this is the preminum for going to the best in class IGU, granted way out in the guture but the contractor grade to preminum factor has existed foever.
| Electric Boiler - Clearwave mitigation | Electrificaiton | Electrification | 3007004 | Capex | 2035 | Cost is incremential for going to very high efficiency IGU's
[6 empty] | 3040 | Stem entrace in is basment cannot put ASHP on roof electric boiler is only option. Scheduling out to see what Clearwave does.
400 Castro
| Retrocommissioning (RCx) | Complete BMS commissioning | Retrofit | 24977.16 | R&M | 2027 | Timed on leasing
| Façade air stopping | caulking and general air stopping | Retrofit | 289000 | R&M | 2035 | Timing based on EOL for sealents
| ASHPHW system to replace boilers | Electrificaiton | Electrification | 2300000 | Capex | 2030 | Another textbook installation and application. Timing based on leasing, and ease of job
520 Pike
| Retrocommissioning (RCx) | Complete BMS commissioning | Retrofit | 51000 | R&M | 2026 | Could be 2025, recommend we do in 2026 because of an HR issue that is being worked.
| Elevator energy revovery | Optional add to elevator package | Capital Project Enhancement | 68000 | Capex | 2030 | based on next mod
| Controls expansion | Optimization Controls | Retrofit | 105000 | Capex | 2027 | This has been happening on lease turns the point having it here is the keep the program rolling. All installations are leasing dependent. This is the cost to finish as of 2024, hense scheduleing it for 2027
| Pneumatic Converstion | VAV Boxes | Retrofit | 750000 | Capex | 2024 | This has been happening on lease turns the point having it here is the keep the program rolling. All installations are leasing dependent. This is the cost to finish as of 2024, hense scheduleing it for 2027
Brickyard
No recommendations at this site - it is already all efficient electric. The main goal will be to maintain operations at the high level of efficiency are currently are at.
Arboretum Courtyard
| Retrocommissioning (RCx) | Complete BMS commissioning | Retrofit | 15840 | R&M | 2026
| DHW to Point of Use | Electrificaiton | Electrification | 231000 | Capex | 2030 | Timed for leasing rolls
| ASHPHW system to replace boilers | Electrificaiton | Electrification | 2195000 | Capex | 2030 | Another textbook installation and application. Timing based on leasing, and ease of job
Beverly Place
| Retrocommissioning (RCx) | Complete BMS and condenser | Retrofit | 88200 | R&M | 2027 | This is timed to occure after leasing changes
6430 Sunset
| Façade air stopping | Caulking and general air stopping | Retrofit | 800000 | R&M | 2030 | scheduled based on sealent life.
| ASHPHW system to replace boilers | Electrificaiton | Electrification | 1965000 | Capex | 2030 | Another textbook installation and application. Timing based on leasing, and ease of job
The Collective
| Retrocommissioning (RCx) | Complete BMS and condenser | Retrofit | 41000 | R&M | 2027 | This is timed to occure after leasing changes